## Trang tính1
Ticket ID | Screen | Element / Component | Required Action | Notes / Constraints
FFIE-01 | Home | Header — Logo area | Add FFIE logo top-left or top-right of the header. Add FFB logo alongside it. Add text below: 'La FFIE est membre adhérent de la FFB'. | Confirm logo placement with client. Both logos must be provided in SVG/PNG @2x.
FFIE-02 | Home | FFIE Logo (tap interaction) | Tapping the FFIE logo opens an infographic screen presenting FFIE key figures (members, coverage, history, etc.). | Infographic content TBD with client. Design a dedicated full-screen or modal view.
FFIE-03 | Home | Quick Access — Member view | Reorder quick-access tiles for logged-in members: Actus / Documentation / Outils FFIE / Partenaires / Trouver un pro. | Order is mandatory. Tiles must match the bottom navigation icons where applicable.
FFIE-04 | Home | Quick Access — Public view | Reorder quick-access tiles for non-logged-in users: Actus / Découvrir les métiers / Trouver un pro. | Public view must not expose member-only sections.
FFIE-05 | Home | Bottom navigation bar | Set the bottom nav tab order to: Accueil / Actus / Docs / Outils / Partenaires / Profil. Each tab must have its icon and label. | 6 tabs total. Verify icon availability for each. 'Profil' tab is new — see FFIE-14.
FFIE-06 | Partners | Partner list | Add FFB as a partner entry in the Partners tab. | Use official FFB logo. Requires logo asset from client.
FFIE-07 | Partners | CONSUEL & QUALIFELEC entries | Visually differentiate CONSUEL and QUALIFELEC from each other and from other partners. They must not appear identical or grouped. | Consider distinct card styling, badges, or a 'Featured' label.
FFIE-08 | Partners | Partner segmentation / tabs | Segment partners into 3 categories displayed as tabs or filter chips: Écosystème / Lab_FFIE / Partenaires FFIE. | Default tab on entry: TBD with client. All 3 segments must be present.
FFIE-09 | Events (Agenda) | Tab label | Rename the 'Évènements' tab to 'Agenda' everywhere it appears. | Update label in bottom nav, screens, and any deep-link references.
FFIE-10 | Agenda | Agenda content | Personalise the Agenda based on user role: standard member, Bureau member, Board member (Conseil d'administration), etc. Each role sees only the events relevant to their profile. | User roles must be defined and mapped to event categories. Requires back-end role-filtering logic.
FFIE-11 | Outils FFIE | Normes' button | Remove the 'Normes' button. Replace it with a new button labelled 'Références normatives'. | Same position, same visual style. Label change only — verify with dev if it points to a different data source.
FFIE-12 | Outils FFIE | Tool list | Add a new tool card labelled 'Centrale d'achat' to the Outils FFIE screen. | Icon and destination URL/page to be provided by client.
FFIE-13 | Docs | Filter panel | Add a collapsible filter panel on the left side of the screen, placed below the search bar. Filters are closed by default. When a filter group is expanded, the right side of the screen updates to show only documents matching that filter. | Use accordion pattern for filter groups. Filters can be multi-select within a group. Right pane must update on filter change without full page reload.
FFIE-14 | My Profile | New screen | Create a 'Mon Profil' screen accessible from the bottom nav 'Profil' tab. Include: name, role, organisation, contact info, notification settings, and account management. | Screen to be defined in detail with client. Link to Terms of Use from this screen.
FFIE-15 | Actus | Image format | Define and enforce a standard image format for news articles. Images must scale proportionally (aspect-ratio preserved, no cropping distortion). Confirm required dimensions and aspect ratio with client (recommended: 16:9 or 3:2). | Document the accepted format in the design system. Add upload validation rules for editors.
FFIE-16 | Map / New feature | Members map | Add a 'Carte des adhérents' feature: a geolocated map of all FFIE members. Include a 'Membres à proximité' list view that lists nearby members based on the user's current location. | Requires geolocation permission prompt. Member data must be opt-in for visibility on the map (GDPR). Define privacy settings in Mon Profil.
FFIE-17 | App-wide | Push notifications | Implement push notification support for members. Notifications triggered by: new Actus, Agenda events, relevant Docs updates, and admin announcements. | Notification preferences managed from Mon Profil (FFIE-14). iOS and Android opt-in flows required.
FFIE-18 | App-wide / Legal | Terms of Use screen | Add a Terms of Use screen defining: display limits, search limits, data usage, and any feature restrictions. Accessible from Mon Profil and onboarding flow. | Content to be written by client/legal team. Designer to provide the screen layout only.
FFIE-19 | App-wide | Offline mode | Decide whether to maintain offline mode. Gather user feedback on current offline behaviour before making a decision. If kept, define which content is cached (Docs, Actus?) and display a clear 'You are offline' indicator. | OPEN QUESTION — requires client input and analytics data. No design work until decision is made.